## Sheet1
Risk Register for "PMBOK Quiz"
No. | Rank | Risk | Description | Category | Root Cause | Potential Responses | Risk Owner | Probability | Impact | Status
1 | 1 | R1 | Inadequate funding to complete project | Resource | Poor cost management plan | Risk Transference | Program Sponsor - Priyanka Galla | Medium | High | Transfered
2 | 2 | R2 | Change in plans about development technologies | Software | Poor quality and resource management plans | Risk Avoidance | Business Analyst - Chitralekha Chikku | Medium | High | Avoided
3 | 3 | R3 | Lack of proper technical skills in team members | Human Resources | Inadequate training provided during initial phase | Risk Mitigation | Technical Team Lead - Divyharshini Bheemireddy | Medium | Medium | Mitigated
4 | 4 | R4 | Unavailability of testing technology software licenses | Software | Poor project management planning | Risk Avoidance | Testing Team Lead - Chitrlekha Chikku | Low | Medium | Avoided
5 | 5 | R5 | Testing malfunctions | Software | Poor testing strategies | Risk Avoidance | Testing Team Lead - Chitrlekha Chikku | Low | Medium | Avoided
6 | 6 | R6 | New requirements add into the scope of project | Human Resources | Poor requirements collection and contract | Risk Acceptance | Project Manager - Priyanka Galla | High | High | Accepted
7 | 7 | R7 | Team member leaves the project | Human Resources | Lack of knowledge transfer between team members on regular basis | Risk Acceptance | Technical Team Lead - Divyharshini Bheemireddy | Low | High | Accepted
8 | 8 | R8 | Loss of project contract due client's lack of confidence | Resource | Lack of experience in stating termination clause | Risk Mitigation | Program Manager - Priyanka Galla | Low | High | Mitigated